## Slide 1: A “Sure Fire” Way to Ensure Schedule Performance!
Mark Hehl
www.hehlassociates.com
mhehl@charter.net
203 982 6231

## Slide 2: Agenda
The Schedule Squeeze
  “Parkinson’s Law”
Improving Schedule Performance
The Key Improvement Tool
Using Process Mapping to maintain and reduce scheduled tasks
Implementing Improvements
Identifying Processes to map
Getting Started

## Slide 3: Parkinson’s Law
“The time required to perform a task will automatically expand to fill the time allotted for it”.

## Slide 4: “I will give you anything but more time”
Most schedules fall behind
  Unrealistic
  Resources
  Unanticipated events
  Delays
  Negative consequences

## Slide 5: The Schedule Challenge
Challenging - Realistic
  Motivation issue
History Repeats Itself
  Consistent areas / tasks / causes

## Slide 6: The Reactions Do Not Need To Be Negative!
Schedule slippage added cost
  Cutting corners risk increase
Additional resources added cost
  People
  Time
Problem area/s process improvement
  No added cost
  No risk increase

## Slide 7: A Positive Reaction - Process Improvement
Identify areas / tasks that typically cause schedule problems
  Most cases - problem is with a few processes
Understand the process
Analyze the process
Identify improvements
Implement improvements
Control / follow up

## Slide 8: The First Step Towards Improvement - Process Mapping
-Visually depicts the sequence of events to build a product or produce an outcome.
1) understand the process
2) Analyze
3) Improve

## Slide 9: Process Map
A defined graphical representation of a process showing the:
  Steps of the process
  Time & Cost
  Inputs and outputs for each step
  Suppliers and customers
  Media used
  Issues in present process

## Slide 10: Process Mapping Sessions Capture
Non-value added activities
Delay points in the process
Cumbersome forms
Lack of supporting documentation and information
Lack of understanding
Inconsistency

## Slide 11: “Quick Wins” - Value Added vs. Non-Value Added
Within an average American organization, less than 25% of the company’s time and effort is spent on value-added activities.
More than 60% is spent on activities that consume time and create cost without creating any value.

## Slide 12: Proceeding with Process Mapping
Group activity
  Individuals performing the activity
  True experts
“as is” map
Cards attached to wall
  Elapsed time
  Labor hours
  Cost
  Defects

## Slide 13: Example
Add photo of a process map in process,
Index cards on wall

## Slide 15: Swimlane - Process Map

## Slide 16: $4 Million Annual Savings
Unintentional outcome (Quick Win)
New customer orders
Dual inventory assessments
Duplicate ordering of expensive material
Results
  Reduce inventory
  Faster process time
  Increased space for actual work
  8 extra hours/week available for preventative work

## Slide 17: Achieving Results
Analyze each step
Select significant steps
Improve
Implement
Measure results

## Slide 18: Schedule Improvement - Getting Started
Team
  Those involved – the real experts!
Facilitator
  Trained
  Experienced
Room with available walls
Large Index Cards

## Slide 19: You Must Have a Trained Facilitator
A trained & experienced facilitator is a requirement
Most common reason for failure!
  Inadequate facilitation skill

## Slide 20: Benefits
Increases speed
  – Schedule Compliance
Lowers cost
Improves quality
Enhances productivity
Allows the workforce to contribute
  Motivation
  Buy-in
  Teamwork

## Slide 21: Questions?
Thank you for allowing me to be of service!
Mark Hehl
www.hehlassociates.com
203 982 6231
Mhehl@charter.net